## Sheet1
Defect ID | Module | Defect Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
DEF_01 | Cart | Order total is not updated when product quantity is changed in cart | 1. Login as registered user 2. Add a product to cart 3. Navigate to cart page 4. Change product quantity 5. Observe product total | Order total should update according to the selected quantity | Order total remains unchanged after quantity update | Major | High | New
DEF_02 | Login | Validation message not displayed when login fields are left empty | 1. Navigate to login page 2. Leave email and password fields empty 3. Click on login button | Validation message should be displayed for required fields | No validation message is displayed and login action is attempted | Minor | Medium | New
DEF_03 | Checkout | Order can be placed without selecting a payment method during checkout | 1. Login as registered user 2. Add a product to cart 3. Navigate to checkout page 4. Do not select any payment method 5. Click on place order | System should restrict order placement and display validation for payment method | Order is placed successfully without selecting any payment method | Critical | High | New
DEF_04 | Registration | Registration allows weak password without displaying validation message | 1. Navigate to registration page 2. Enter valid user details 3. Enter weak password 4. Click Register | System should restrict registration and show password validation message | Registration proceeds without password validation | Major | High | New
DEF_05 | Product Search | No “No results found” message displayed for invalid product search | 1. Navigate to home page 2. Enter invalid product name in search bar 3. Click Search | System should display a clear “No results found” message | Search results page appears without any informative message | Minor | Medium | New
DEF_06 | Wishlist | No confirmation message or visual indication displayed after adding product to wishlist | 1. Login as registered user 2. Navigate to product listing page 3. Click wishlist icon for a product | Confirmation message or visual indicator should be displayed | No confirmation or visual feedback is displayed | Minor | Medium | New